Special Conditions of Contract

| GCC Clause |  |
| --- | --- |
| 1.16 | The Intended Completion Date is 36 Months (1095 calendar days) inclusive of unworkable days. |
| 1.21 | The Procuring Entity is Philippine Statistics Authority PSA-CVEA Building, East Avenue, Diliman, Quezon City |
| 1.22 | The Procuring Entity’s Representative is : LISA GRACE S. BERSALES, Ph.D National Statistician Philippine Statistics Authority ` |
| 1.23 | The Site is located at East Avenue and is defined in drawings No. [Sheet A-101]. |
| 1.27 | The Start Date is seven (7) calendar days from the issuance of Notice to Proceed. |
| 1.30 | The Work shall consist of the Construction of 23-storey PSA Building with roof deck.[refer to Architectural Drawings]. |
| 2.2 | No further instructions. |
| 5.1 | The Procuring Entity shall give possession of all parts of the Site to the Contractor beginning on the effective date of the contract until the date of the termination and/or project completion. |
| 6.5 | The Contractor shall employ at least the following Key Personnel: Project Manager Project Engineer Resident Structural Engr QA/QC/ Materials Engr II ( Materials Engr II as per DPWH Standard) Resident Architect Geodetic Engineer (Surveyor) Electrical engineer Mechanical Engineer Sanitary Engineer ECE Quantity surveyor Site Supervisors Safety Officer |
| 7.4 (c ) | “No further instructions”. |
| 7.7 | No further instructions. |
| 8.1 | No further instructions. |
| 10 | The bidder is required to Conduct Inspection of Site to verify site actual condition and submit together with the Bid the Notarized Affidavit of Site Inspection. |
| 12.3 | No further instructions. |
| 12.5 | 15 years |
| 13 | If the Contractor is a joint venture, “All partners to the joint venture shall be jointly and severally liable to the Procuring Entity.” |
| 15.1(a) | Contractor’s All Risk Insurance (CARI) shall be submitted by the contractor as part of the requirements for contract facilitation. |
| 18.3(h)(i) | No further instructions. |
| 21.2 | The Arbiter is: Construction Industry Arbitration Commission 5th Floor, Executive Building, Corner Buendia, Makati City |
| 29.1 | Dayworks are applicable at the rate shown in the Contractor’s original Bid. |
| 31.1 | The Contractor shall submit the Program of Work to the Procuring Entity’s Representative within ten(10) calendar days of from receipt of Notice of Award. |
| 31.3 | The period between Program of Work updates is 7 to 15 days. The amount to be withheld for late submission of an updated Program of Work is 5% of the contract amount. |
| 34.3 | The Funding Source is the Government of the Philippines through its 2016 GAA and MYOA for 2016-2019. |
| 39.1 | The amount of the advance payment is 15% of the contract amount. |
| 51.1 | The date by which “as built” drawings are required is 15 days after project completion. |
| 51.2 | The final payment shall be withheld for failing to produce “as built” drawings. |